## Notes
This is a reference document with some data filled in as sample content.
Detailed Internship Plan sheet - Weekly activity: Hands on / Deliverables can be added along with detailed Functional/ NonFunctional Delivery etc
Remarks and Scores has to be filled by the mentor on a scale of 10 every week and share to corporate through TD team.
Task Planner & Summary sheet has to be filled up & maintain appropriately through out 12 Weeks
Mentor has to provide the weekly feedback or remarks and scores out of 10 and the same has to be captured appropriately in the Summary Sheet. Also ensured to capture Mentor Remarks and Mentee Remarks in the Task Planner sheet
Performance issues with the assocaites, if any, needs to be informed within the first 4 weeks of starting the program.
Some data may have to be repeated across different sheets for tracking of progress.

## Summary & Allocation Details
Associate Progress Status - score out of 10
Emp ID | Emp Name | Emp Grade | Mentor ID | Mentor Name | Current Child IOU | Account / PoC/ Project Name | BG | Tech Stack | Start Date | End Date | WON for 1% Allocation | Week 1 Score out of 10 | Remark | Week 2 Score out of 10 | Remark | Week 3 Score out of 10 | Remark | Week 4 Score out of 10 | Remark | Week 5 Score out of 10 | Remark | Week 6 Score out of 10 | Remark | Week 7 Score out of 10 | Remark | Week 8 Score out of 10 | Remark | Week 9 Score out of 10 | Remark | Week 10 Score out of 10 | Remark | Week 11 Score out of 10 | Remark | Week 12 Score out of 10 | Remark
2877956 | Abhishek Saw | C1 | 327539 | Amit Paul |  |  | LSHC | Java Full Stack
2863529 | Mr. Sagnik Kolay | C1 | 327539 | Amit Paul |  |  | LSHC | Java Full Stack
2877914 | Ashish Kumar Singh | C1 | 327539 | Amit Paul |  |  | LSHC | Java Full Stack
2909637 | Mr. Mantosh Kumar | C1 | 327539 | Amit Paul |  |  | LSHC | Java Full Stack
2858380 | Mr. Md Shakir | C1 | 327539 | Amit Paul |  |  | LSHC | Java Full Stack

## List of requirements
Complexity | Objective | Component Type | Module Number | Module Name | Problem description | Definition of Done | Definition of Ready
Medium | Enable patient registration with demographic details | UI + Service | 1 | Patient Registration & Demographics | Manual registration leads to errors and delays | JSP form implemented, Hibernate persistence, SOAP service exposed → Provides a digital registration form, automated data storage, and external system integration, eliminating manual errors and delays. | Frontend Ready: UI mockups finalized; JSP form will include fields for patient name, DOB, gender, address, and contact details. Backend Ready: Database schema finalized, Hibernate mappings prepared. → Ensures technical foundation for storing patient data and UI framework setup.
High | Allow dynamic appointment scheduling and updates | UI + Service | 2 | Appointment Scheduling | No centralized scheduling system | JSP + AJAX slots, Hibernate persistence, SOAP service functional → Enables real-time scheduling, updates, and external queries, solving lack of centralized scheduling. | Frontend Ready: Slot allocation logic defined; JSP page will display calendar view with dynamic time slots and reschedule/cancel buttons. Backend Ready: Appointment table created, Hibernate configuration ready. → Prepares backend structure for dynamic slot allocation.
Medium | Generate invoices and integrate with payment gateway | UI + Service | 3 | Billing & Payment | Manual billing causes delays and errors | JSP dashboard, Hibernate CRUD, JAX-WS integration → Automates invoice generation and payment processing, reducing delays and errors. | Frontend Ready: Billing dashboard developed.SP page will show invoice list, payment status, and “Pay Now” button. Backend Ready: Billing schema finalized, payment gateway API credentials available. → Ensures billing data structure and payment integration readiness.
Medium | Create and track lab orders | UI + Service | 4 | Laboratory Order Management | Lab orders are not tracked digitally | JSP interface, Hibernate persistence, SOAP service → Provides UI for order entry and backend for tracking, solving digital tracking issue. | Frontend Ready: Lab order entry screen design and development completed.JSP page will have test selection dropdown, order status tracker, and submit button. Backend Ready: Lab order schema finalized, Hibernate mappings ready. → Backend ready for storing lab orders.
Medium | Manage prescriptions and refills | UI + Service | 5 | Pharmacy Prescription Management | Prescription handling is manual and error-prone | JSP entry form, Hibernate ORM, JAX-WS drug interaction check → Enables digital prescription entry and safety checks, reducing errors. | Frontend Ready: Prescription entry and refill UI developed.JSP page will include drug name input, dosage fields, and refill request option. Backend Ready: Prescription schema finalized, drug interaction API accessible. → Prepares backend and external API for safe prescription handling

## Project Plan
Emp ID | Emp Name | Week | Module Number | Task Name | Description
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 1 | 1 | Requirement Analysis & DB Schema Design | Analyze requirements and design DB schema. DoD: Approved schema. DoR: Requirements finalized.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 2 | 1 | UI Development (JSP + Struts Form Bean) | Develop JSP pages and Struts Form Bean. DoD: UI screens functional. DoR: UI mockups ready.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 3 | 1 | Input Validation Setup | Implement Struts Validator for input checks. DoD: Validation rules applied. DoR: Validation specs ready.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 4 | 1 | Hibernate ORM Integration | Integrate Hibernate for persistence. DoD: CRUD operations working. DoR: DB schema available.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 5 | 1 | Service Layer Development (JAX-WS) | Develop SOAP service for module. DoD: Service deployed. DoR: WSDL contract ready.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 6 | 1 | Unit & Integration Testing | Perform unit and integration tests. DoD: All tests passed. DoR: Test cases prepared.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 7 | 1 | HL7 Message Implementation | Implement HL7 message exchange. DoD: HL7 messages sent successfully. DoR: HL7 specs available.
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | Week 8 | 1 | Final Review & Deployment | Review and deploy module. DoD: Deployment completed. DoR: UAT sign-off received.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 1 | 2 | Requirement Analysis & DB Schema Design | Analyze requirements and design DB schema. DoD: Approved schema. DoR: Requirements finalized.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 2 | 2 | UI Development (JSP + Struts Form Bean) | Develop JSP pages and Struts Form Bean. DoD: UI screens functional. DoR: UI mockups ready.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 3 | 2 | Input Validation Setup | Implement Struts Validator for input checks. DoD: Validation rules applied. DoR: Validation specs ready.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 4 | 2 | Hibernate ORM Integration | Integrate Hibernate for persistence. DoD: CRUD operations working. DoR: DB schema available.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 5 | 2 | Service Layer Development (JAX-WS) | Develop SOAP service for module. DoD: Service deployed. DoR: WSDL contract ready.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 6 | 2 | Unit & Integration Testing | Perform unit and integration tests. DoD: All tests passed. DoR: Test cases prepared.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 7 | 2 | HL7 Message Implementation | Implement HL7 message exchange. DoD: HL7 messages sent successfully. DoR: HL7 specs available.
2858380 | Md Shakir <md.shakir2@tcs.com> | Week 8 | 2 | Final Review & Deployment | Review and deploy module. DoD: Deployment completed. DoR: UAT sign-off received.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 1 | 3 | Requirement Analysis & DB Schema Design | Analyze requirements and design DB schema. DoD: Approved schema. DoR: Requirements finalized.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 2 | 3 | UI Development (JSP + Struts Form Bean) | Develop JSP pages and Struts Form Bean. DoD: UI screens functional. DoR: UI mockups ready.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 3 | 3 | Input Validation Setup | Implement Struts Validator for input checks. DoD: Validation rules applied. DoR: Validation specs ready.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 4 | 3 | Hibernate ORM Integration | Integrate Hibernate for persistence. DoD: CRUD operations working. DoR: DB schema available.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 5 | 3 | Service Layer Development (JAX-WS) | Develop SOAP service for module. DoD: Service deployed. DoR: WSDL contract ready.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 6 | 3 | Unit & Integration Testing | Perform unit and integration tests. DoD: All tests passed. DoR: Test cases prepared.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 7 | 3 | HL7 Message Implementation | Implement HL7 message exchange. DoD: HL7 messages sent successfully. DoR: HL7 specs available.
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | Week 8 | 3 | Final Review & Deployment | Review and deploy module. DoD: Deployment completed. DoR: UAT sign-off received.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 1 | 4 | Requirement Analysis & DB Schema Design | Analyze requirements and design DB schema. DoD: Approved schema. DoR: Requirements finalized.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 2 | 4 | UI Development (JSP + Struts Form Bean) | Develop JSP pages and Struts Form Bean. DoD: UI screens functional. DoR: UI mockups ready.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 3 | 4 | Input Validation Setup | Implement Struts Validator for input checks. DoD: Validation rules applied. DoR: Validation specs ready.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 4 | 4 | Hibernate ORM Integration | Integrate Hibernate for persistence. DoD: CRUD operations working. DoR: DB schema available.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 5 | 4 | Service Layer Development (JAX-WS) | Develop SOAP service for module. DoD: Service deployed. DoR: WSDL contract ready.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 6 | 4 | Unit & Integration Testing | Perform unit and integration tests. DoD: All tests passed. DoR: Test cases prepared.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 7 | 4 | HL7 Message Implementation | Implement HL7 message exchange. DoD: HL7 messages sent successfully. DoR: HL7 specs available.
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | Week 8 | 4 | Final Review & Deployment | Review and deploy module. DoD: Deployment completed. DoR: UAT sign-off received.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 1 | 5 | Requirement Analysis & DB Schema Design | Analyze requirements and design DB schema. DoD: Approved schema. DoR: Requirements finalized.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 2 | 5 | UI Development (JSP + Struts Form Bean) | Develop JSP pages and Struts Form Bean. DoD: UI screens functional. DoR: UI mockups ready.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 3 | 5 | Input Validation Setup | Implement Struts Validator for input checks. DoD: Validation rules applied. DoR: Validation specs ready.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 4 | 5 | Hibernate ORM Integration | Integrate Hibernate for persistence. DoD: CRUD operations working. DoR: DB schema available.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 5 | 5 | Service Layer Development (JAX-WS) | Develop SOAP service for module. DoD: Service deployed. DoR: WSDL contract ready.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 6 | 5 | Unit & Integration Testing | Perform unit and integration tests. DoD: All tests passed. DoR: Test cases prepared.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 7 | 5 | HL7 Message Implementation | Implement HL7 message exchange. DoD: HL7 messages sent successfully. DoR: HL7 specs available.
2877914 | Ashish Singh <ashish.singh@tcs.com> | Week 8 | 5 | Final Review & Deployment | Review and deploy module. DoD: Deployment completed. DoR: UAT sign-off received.

## Task tracker
Emp ID | Emp Name | Mentor ID | Mentor Name | PoC/Project Name | Week | Task Name | Tech Stack | Status | Mentee Remarks | Mentor Remarks
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 1 | Requirement Analysis & DB Schema Design | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 2 | UI Development (JSP + Struts Form Bean) | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 3 | Input Validation Setup | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 4 | Hibernate ORM Integration | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 5 | Service Layer Development (JAX-WS) | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 6 | Unit & Integration Testing | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 7 | HL7 Message Implementation | Java Full Stack
2863529 | Sagnik Kolay <kolay.sagnik@tcs.com> | 327539 | Amit Paul | Patient Registration & Demographics | Week 8 | Final Review & Deployment | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 1 | Requirement Analysis & DB Schema Design | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 2 | UI Development (JSP + Struts Form Bean) | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 3 | Input Validation Setup | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 4 | Hibernate ORM Integration | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 5 | Service Layer Development (JAX-WS) | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 6 | Unit & Integration Testing | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 7 | HL7 Message Implementation | Java Full Stack
2858380 | Md Shakir <md.shakir2@tcs.com> | 327539 | Amit Paul | Appointment Scheduling | Week 8 | Final Review & Deployment | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 1 | Requirement Analysis & DB Schema Design | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 2 | UI Development (JSP + Struts Form Bean) | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 3 | Input Validation Setup | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 4 | Hibernate ORM Integration | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 5 | Service Layer Development (JAX-WS) | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 6 | Unit & Integration Testing | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 7 | HL7 Message Implementation | Java Full Stack
2877956 | Abhishek Shaw <abhishek.shaw3@tcs.com> | 327539 | Amit Paul | Billing & Payment | Week 8 | Final Review & Deployment | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 1 | Requirement Analysis & DB Schema Design | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 2 | UI Development (JSP + Struts Form Bean) | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 3 | Input Validation Setup | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 4 | Hibernate ORM Integration | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 5 | Service Layer Development (JAX-WS) | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 6 | Unit & Integration Testing | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 7 | HL7 Message Implementation | Java Full Stack
2909637 | Mantosh Kumar <mantosh.k9@tcs.com> | 327539 | Amit Paul | Laboratory Order Management | Week 8 | Final Review & Deployment | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 1 | Requirement Analysis & DB Schema Design | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 2 | UI Development (JSP + Struts Form Bean) | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 3 | Input Validation Setup | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 4 | Hibernate ORM Integration | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 5 | Service Layer Development (JAX-WS) | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 6 | Unit & Integration Testing | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 7 | HL7 Message Implementation | Java Full Stack
2877914 | Ashish Singh <ashish.singh@tcs.com> | 327539 | Amit Paul | Pharmacy Prescription Management | Week 8 | Final Review & Deployment | Java Full Stack

## Detailed Plan Java Full Stack
Week No: | Weekly Agenda | Functional Delivery (Include Frontend/Backend) | Non Functional Delivery | Evaluation Criteria if any
1 | Requirement Analysis & DB Schema Design | Backend – Database schema design | Requirements documentation | Approved schema and requirement sign-off
2 | UI Development (JSP + Struts Form Bean) | Frontend – JSP pages; Backend – Struts integration | UI mockups reviewed | UI screens functional and reviewed
3 | Input Validation Setup | Backend – Validation logic; Frontend – Error messages | Validation specs documented | All validation rules tested
4 | Hibernate ORM Integration | Backend – CRUD operations | ORM configuration documented | CRUD operations successful
5 | Service Layer Development (JAX-WS) | Backend – SOAP service implementation | WSDL contract published | Service deployed and tested
6 | Unit & Integration Testing | Backend – Test cases executed | Test report generated | All tests passed
7 | HL7 Message Implementation | Backend – HL7 message generation | HL7 specs compliance check | HL7 messages validated
8 | Final Review & Deployment | Frontend & Backend – Final deployment | UAT sign-off | Deployment completed successfully